## Component
SL | Date | Targets | Task | Remarks | Assign Person | Link
1 | 2021-01-01 | weekend
2 | 2021-01-02 | weekend
3 | 2021-01-03 | Workshop |  |  | Riyad
4 | 2021-01-04 | Workshop |  |  | Riyad, Polash
5 | 2021-01-05 | Integration Scope Findings & Prepare & Submit Draft Document | Integration Point Identification | Integration Point (Pull -push Data)/Capture all data/field Link with Integration Tab | Riyad | Integration Sheet
6 | 2021-01-06 |  | Integration Point Identification |  | Riyad
7 | 2021-01-07 |  | Integration Point Identification |  | Riyad
8 | 2021-01-08 | weekend
9 | 2021-01-09 | weekend
10 | 2021-01-10 | RTM Based Module Wise Prototype Design (Label Findings, Data Flow,control flow, Report Format Collection, etc.) | Module 1 & 2
11 | 2021-01-11 |  | Module 1 & 2 |  | Polash
12 | 2021-01-12 |  | Module 1 & 2
13 | 2021-01-13 |  | Module 1 & 2
14 | 2021-01-14 |  | Module 1 & 2
15 | 2021-01-15 | weekend
16 | 2021-01-16 | weekend
17 | 2021-01-17 | RTM Based Module Wise Prototype Design (Label Findings, Data Flow,controlflow etc.) | Module 3,4 & 5
18 | 2021-01-18 |  | Module 3,4 & 5
19 | 2021-01-19 |  | Module 3,4 & 5
20 | 2021-01-20 | Finding the Output Scope of the System | Module 3,4 & 5
21 | 2021-01-21 |  | Module 3,4 & 5
22 | 2021-01-22 | weekend
23 | 2021-01-23 | weekend
24 | 2021-01-24 | Merging Above all Task and Prepared Draft SRS,SDD,GIS Map requirment documents | Component 2 Detail Document Prepration
25 | 2021-01-25 |  | Component 2 Detail Document Prepration
26 | 2021-01-26 |  | Component 2 Detail Document Prepration
27 | 2021-01-27 |  | Document Merge
28 | 2021-01-28 |  | Document Merge
29 | 2021-01-29 | weekend
30 | 2021-01-30 | weekend
31 | 2021-01-31 | Peer Review & Merging Component Wise | Review
32 | 2021-02-01 | Delivery | Draft SRS.SDD,GIS Map Requriment document Submission

## Question
Sl | Component Name | Business Requirement (BR) | Question | Answer | Relation with Module | Remarks
|  | Last Plan Implementation Review | How to review the last plan Success with Target growth and Acieved growth ?
Why are using the Last Plan Success history ?
When will the last plan review start?
By Whom the last success plan were made?
What are the reasons of reviewing last plan success?
Where do we do the review of last plan success?

## C2-RTM
BR_ID | Business Requirement | FR_ID | Functional Requirement | Actor/Stakeholder | Relationship Between Internal FR | Relationship Between External FR | NFR_ID | NFR | Relationship Between FR & NFR | Mockup Ref. | Remarks
BR-C5-M5-00001 | Api Management | BR-C5-M5-00001-FR-01_(Ref.) | APIs will be categorized as private/internal and public/external. | S. Admin, Admin, Component wise users | BR-C5-M4-00001-FR-00002 |  |  |  |  | MOC-C5-M4-00001
|  | BR-C5-M5-00001-FR-02_(Ref.) | Private APIs will be distributed with ROLE along with respect to jwt and sso. | S. Admin, Admin, Component wise users | BR-C5-M3-00002-FR-00001
|  | BR-C5-M5-00001-FR-03_(Ref.) | Public APIs will be exposed to certain registered company/organization. | S. Admin, Admin, Component wise users | BR-C5-M4-00001-FR-00002
|  | BR-C5-M5-00001-FR-04_(Ref.) | company/organization can register as external API consumer. (Create operation) | S. Admin, Admin, Component wise users | [5 empty] | MOC-C5-M5-00001
|  | BR-C5-M5-00001-FR-05_(Ref.) | company/organization can modify, pause API access as external API consumer. (Update operation) | S. Admin, Admin, Component wise users
|  | BR-C5-M5-00001-FR-06_(Ref.) | Admin can block & manage company/organization’s access using an admin dashboard. (Update operation) | S. Admin, Admin, Component wise users | [5 empty] | MOC-C5-M5-00002
|  | BR-C5-M5-00001-FR-07_(Ref.) | Admin can block & manage company/organization’s access using an admin dashboard. (Update operation) | S. Admin, Admin, Component wise users
BR-C5-M5-00002 | Secure API Management | BR-C5-M5-00002-FR-01_(Ref.) | After registration a unique CLIENT ID and API KEY will be sent to registered users/company using e-mail from the registration. | S. Admin, Admin, Component wise users
|  | BR-C5-M5-00002-FR-02_(Ref.) | User/company will use this API KEY to consume these public APIS. | S. Admin, Admin, Component wise users
S. Admin, Admin, Component wise users
BR-C5-M6-00001 | Notification Settings Management | BR-C5-M6-00001-FR-01_(Ref.) | Admin can create Notification rules(From Component’ module to multiple component’s module) using notification settings. | S. Admin, Admin, Component wise users |  | Configurable Data |  |  |  | MOC-C5-M6-00001
|  | BR-C5-M6-00001-FR-02_(Ref.) | Admin can update Notification rules using notification settings. | S. Admin, Admin, Component wise users
|  | BR-C5-M6-00001-FR-03_(Ref.) | Admin can delete Notification rules using notification settings. | S. Admin, Admin, Component wise users
|  | BR-C5-M6-00001-FR-04_(Ref.) | Notification will have unique code generated from each component combined with tag using notification settings. | S. Admin, Admin, Component wise users
|  | BR-C5-M6-00001-FR-05_(Ref.) | Notification rules will contain which service/component receive the notifications. | S. Admin, Admin, Component wise users
BR-C5-M6-00002 | Notification Medium | BR-C5-M6-00002-FR-01_(Ref.) | Specific dynamic notification will be generated by system in various system events and published to the selected recipient’s component’s users from the notification rules. | S. Admin, Admin, Component wise users
|  | BR-C5-M6-00002-FR-02_(Ref.) | The notifications will use different medium according to BR-C5-M6. | S. Admin, Admin, Component wise users
|  | BR-C5-M6-00002-FR-03_(Ref.) | Every notification will need to be saved with unique notification_id. | S. Admin, Admin, Component wise users
BR-C5-M6-00003 | Notification Types | BR-C5-M6-00003-FR-03_(Ref.) | Different types of dynamic notification settings can be created using notification type which will be used in notification generation. | S. Admin, Admin, Component wise users
|  | BR-C5-M6-00003-FR-01_(Ref.) | Create new different notification type. | S. Admin, Admin, Component wise users | [5 empty] | MOC-C5-M6-00002
|  | BR-C5-M6-00003-FR-04_(Ref.) | list different notification type. | S. Admin, Admin, Component wise users
|  | BR-C5-M6-00003-FR-05_(Ref.) | Update different notification type. | S. Admin, Admin, Component wise users
BR-C6-M6-00004 | Notification Template Management | BR-C5-M6-00004-FR-01_(Ref.) | Notification will be generated & send using notification template. Two different templates will be needed. SMS template & E-mail template | S. Admin, Admin, Component wise users | BR-C5-M2-00001-FR |  |  |  |  | MOC-C5-M6-00003
|  | BR-C5-M6-00004-FR-01_(Ref.) | Every notification will be saved after it is generated from template. | S. Admin, Admin, Component wise users | [5 empty] | MOC-C5-M6-00004
BR-C5-M6-00005 | Notification Scheduler | BR-C5-M6-00005-FR-01_(Ref.) | User will set time and occurrence type for each notification. | S. Admin, Admin, Component wise users | [5 empty] | MOC-C5-M6-00005
|  | BR-C5-M6-00005-FR-02_(Ref.) | Create time schedule and occurrence type for notifications. | S. Admin, Admin, Component wise users
|  | BR-C5-M6-00005-FR-03_(Ref.) | Update time schedule and occurrence type for notifications. | S. Admin, Admin, Component wise users
BR-C5-M6-00006 | Notification History Management | BR-C6-M6-00006-FR-01_(Ref.) | There will have a list for all the generated notifications. | S. Admin, Admin, Component wise users | [5 empty] | MOC-C5-M6-00006
|  | BR-C6-M6-00006-FR-02_(Ref.) | Users can filter these previously generated notifications efficiently with different filter types. | S. Admin, Admin, Component wise users
BR-C5-M4-00001 | Multi-Layer Access Control | BR-C5-M4-00001-FR-00001 | Selecting component wise module and set endpoint, mode and type | Admin | [5 empty] | MOC-C5-M4-00001
|  | BR-C5-M4-00001-FR-00002 | Save, update, delete the api | Admin
|  | BR-C5-M4-00001-FR-00003 | For any component by selecting module set multiple api for this role | Admin | BR-C5-00002-FR-00001 |  |  |  |  | MOC-C5-M4-00002
|  | BR-C5-M4-00001-FR-00004 | Remove any number of api for this role and save. | Admin
|  | BR-C5-M4-00001-FR-00005 | Get all types of activities by searching component. | Admin
BR-C5-M4-00002 | Factor Authentication (need to write in role/access) | BR-C5-M4-00002-FR-00001 | A dropdown list for all users. | Admin | [5 empty] | MOC-C5-M4-00003
|  | BR-C5-M4-00002-FR-00002 | Select user for edit 2F/A setup | Admin
|  | BR-C5-M4-00002-FR-00003 | Enable or disable 2F/A for selected user from dropdown | Admin
|  | BR-C5-M4-00002-FR-00004 | The 2F/A enabled user need to login with password and OTP code from via text message or using a token as a security key | Admin
BR-C5-M4-00003 | For maintain this component 2, need some master data that use time to time into this system | BR-C5-M4-00003-FR-00001 | It provides to user to access all of assigned systems with single credential. | Unseen | [5 empty] | MOC-C5-M4-00004
|  | BR-C5-M4-00003-FR-00002 | E-Nothi user can access all assigned systems by single login | Unseen
|  | BR-C5-M4-00003-FR-00003 | No multiple access credentials needed to access multiple systems | Unseen
BR-C5-M3-00001 | User Account Management | BR-C5-M3-00001-FR-00001 | Admin can create new user. | Admin |  |  | MOC-C5-M3-00001
|  | BR-C5-M3-00001-FR-00002 | Admin can view list of users. | Admin |  |  | MOC-C5-M3-00002
|  | BR-C5-M3-00001-FR-00003 | Admin can update user. | Admin
|  | BR-C5-M3-00001-FR-00004 | Admin can block user. | Admin
|  | BR-C5-M3-00001-FR-00005 | Admin can delete user. | Admin
|  | BR-C5-M3-00001-FR-00006 | Admin can assign designated roles with their designation. | Admin | BR-C5-M2-00001-FR-00001
|  | BR-C5-M3-00001-FR-00007 | Admin can edit user designation. | Admin | BR-C5-M2-00001-FR-00001
BR-C5-M3-00002 | User Role Management | BR-C5-M3-00002-FR-00001 | Admin can create new role. | Admin |  |  | MOC-C5-M3-00003
|  | BR-C5-M3-00002-FR-00002 | Admin can view List of users. | Admin
|  | BR-C5-M3-00002-FR-00003 | Admin can update role. | Admin
|  | BR-C5-M3-00002-FR-00004 | Admin can delete role. | Admin
BR-C5-M3-00003 | User Account Verification | BR-C5-M3-00003-FR-00001 | Send verification code through email or sms. |  |  |  | MOC-C5-M3-00004
BR-C5-M3-00004 | User Account Recovery | BR-C5-M3-00004-FR-00001 | User can Recover their account by using email or secret question or sms. System will send recovery code. |  |  |  | MOC-C5-M3-00005
BR-C5-M3-00005 | Change Password | BR-C5-M3-00005-FR-00001 | User can change their password any time for security purpose. |  |  |  | MOC-C5-M3-00006
BR-C5-M3-00006 | Profile Management | BR-C5-M3-00006-FR-00001 | User can update their account information such as mobile no, photo, signature, email, password etc. |  |  |  | MOC-C5-M3-00007

## Integration
Sl | Integration Point | Is System Ready? | Push/Pull | Internal/External | Who are Using It | Why Using It | How Using It | What Are The Output | When Use It | Remarks
1 | Bangladesh Bureau of Statistics (BBS) | Yes | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document | Initialize of the Next Plan
2 | Bangladesh Bank (BB) |  | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
3 | Bangladesh Bureau of Educational Information and Statistics (BANBEIS) |  | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
4 | National Board of Revenue (NBR) |  | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
5 | SMS Gateway |  | Both |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
6 | iBas++ |  | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
7 | Input Output Table (IOT) |  |  |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
8 | Social Accounting Matrix (SAM) |  |  |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
9 | e-Nothi |  | Both |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
10 | National Platform Framework (NPF) |  |  |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document

## Common Service
Sl | Common Service Name | Related Component Module | Remarks

## Report
SL | Module | Report Name | Business Rules | Format

## WS_Int_Q
Sl | Integration Point | Is System Ready? | Push/Pull | Internal/External | Who are Using It | Why Using It | How Using It | What Are The Output | When Use It | Remarks

## SRS Checklist
Sl | Title | Status | Remarks