## Component
SL | Date | Targets | Task | Remarks | Assign Person | Link
1 | 2021-01-01 | weekend
2 | 2021-01-02 | weekend
3 | 2021-01-03 | Workshop |  |  | Riyad
4 | 2021-01-04 | Workshop |  |  | Riyad, Polash
5 | 2021-01-05 | Integration Scope Findings & Prepare & Submit Draft Document | Integration Point Identification | Integration Point (Pull -push Data)/Capture all data/field Link with Integration Tab | Riyad | Integration Sheet
6 | 2021-01-06 |  | Integration Point Identification |  | Riyad
7 | 2021-01-07 |  | Integration Point Identification |  | Riyad
8 | 2021-01-08 | weekend
9 | 2021-01-09 | weekend
10 | 2021-01-10 | RTM Based Module Wise Prototype Design (Label Findings, Data Flow,control flow, Report Format Collection, etc.) | Module 1 & 2
11 | 2021-01-11 |  | Module 1 & 2 |  | Polash
12 | 2021-01-12 |  | Module 1 & 2
13 | 2021-01-13 |  | Module 1 & 2
14 | 2021-01-14 |  | Module 1 & 2
15 | 2021-01-15 | weekend
16 | 2021-01-16 | weekend
17 | 2021-01-17 | RTM Based Module Wise Prototype Design (Label Findings, Data Flow,controlflow etc.) | Module 3,4 & 5
18 | 2021-01-18 |  | Module 3,4 & 5
19 | 2021-01-19 |  | Module 3,4 & 5
20 | 2021-01-20 | Finding the Output Scope of the System | Module 3,4 & 5
21 | 2021-01-21 |  | Module 3,4 & 5
22 | 2021-01-22 | weekend
23 | 2021-01-23 | weekend
24 | 2021-01-24 | Merging Above all Task and Prepared Draft SRS,SDD,GIS Map requirment documents | Component 2 Detail Document Prepration
25 | 2021-01-25 |  | Component 2 Detail Document Prepration
26 | 2021-01-26 |  | Component 2 Detail Document Prepration
27 | 2021-01-27 |  | Document Merge
28 | 2021-01-28 |  | Document Merge
29 | 2021-01-29 | weekend
30 | 2021-01-30 | weekend
31 | 2021-01-31 | Peer Review & Merging Component Wise | Review
32 | 2021-02-01 | Delivery | Draft SRS.SDD,GIS Map Requriment document Submission

## Question
Sl | Component Name | Business Requirement (BR) | Question | Answer | Relation with Module | Remarks
|  | Last Plan Implementation Review | How to review the last plan Success with Target growth and Acieved growth ?
Why are using the Last Plan Success history ?
When will the last plan review start?
By Whom the last success plan were made?
What are the reasons of reviewing last plan success?
Where do we do the review of last plan success?

## C2-RTM
BR_ID | Business Requirement | FR_ID | FR | NFR_ID | NFR | Relationship Between FR & NFR | Remarks
BR-C5-M7-00001 | Document Store And Management | BR-C5-M7-00001- FR-00001 | Create a from with document name , description etc.
|  | BR-C5-M7-00001- FR-00002 | Upload File with categorize, Tag
|  | BR-C5-M7-00001- FR-00003 | Update document
|  | BR-C5-M7-00001- FR-00004 | Delete document
|  | BR-C5-M7-00001- FR-00005 | Show those documents in table
|  | BR-C5-M7-00001- FR-00006 | Form Validation
BR-C5-M7-00002 | Document Optimization | BR-C5-M7-00002- FR-00001 | Optimize raw documents for system efficient
|  | BR-C5-M7-00002- FR-00002 | Implement optimization with BR-001/ FR-002 when document uploading
BR-C5M7-00003 | Document process and management | BR-C5-M7-00003- FR-00001 | Show expected Input field by chosen template.
|  | BR-C5-M7-00003- FR-00002 | Display Form for Certificate Template
|  | BR-C5-M7-00003- FR-00003 | Form Validation for Certificate Template
|  | BR-C5-M7-00003- FR-00004 | Display Form for approval latter
|  | BR-C5-M7-00003- FR-00005 | Form Validation for Approval Latter
|  | BR-C5-M7-00003- FR-00006 | Display Form for Testimonial
|  | BR-C5-M7-00003- FR-00007 | Form Validation for Testimonial
|  | BR-C5-M7-00003- FR-00008 | Show those document in table
BR-C5-M7-00004 | Document template management | BR-C5-M7-00004- FR-00001 | Make Default Template for Certificate
|  | BR-C5-M7-00004- FR-00002 | Make Default Template for approval latter
|  | BR-C5-M7-00004- FR-00003 | Make Default Template for Testimonial
|  | BR-C5-M7-00004- FR-00004 | Setup template type like doc,pdf,etc
BR-C5-M7-00005 | Document verification management | BR-C5-M7-00005- FR-00001 | Get List of documents
|  | BR-C5-M7-00005- FR-00002 | Show those in table with approval option
|  | BR-C5-M7-00005- FR-00003 | Show approve symbol in BR-001/ FR-005
BR-C5-M7-00006 | Document meta data management | BR-C5-M7-00006- FR-00001 | Add New Document Tag
|  | BR-C5-M7-00006- FR-00002 | Delete Document Tag
|  | BR-C5-M7-00006- FR-00003 | Update Document Tag
|  | BR-C5-M7-00006- FR-00004 | Show All Document Tag
|  | BR-C5-M7-00006- FR-00005 | Add New Category
|  | BR-C5-M7-00006- FR-00006 | Delete Category
|  | BR-C5-M7-00006- FR-00007 | Update Category
|  | BR-C5-M7-00006- FR-00008 | Show All Categorize
BR-C5-M7-00007 | Document download and upload management | BR-C5-M7-00007- FR-00001 | Create Document Uploading Form
|  | BR-C5-M7-00007- FR-00002 | Show list of uploaded document in table
|  | BR-C5-M7-00007- FR-00003 | Add Download option in FR-002 depending on sensitivity and security of the document.
BR-C5-M7-00008 | Document archiving | BR-C5-M7-00008- FR-00001 | Transfer document into archiving
|  | BR-C5-M7-00008- FR-00002 | Show Archive data by date to date or tag or Category

## Integration
Sl | Integration Point | Is System Ready? | Push/Pull | Internal/External | Who are Using It | Why Using It | How Using It | What Are The Output | When Use It | Remarks
1 | Bangladesh Bureau of Statistics (BBS) | Yes | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document | Initialize of the Next Plan
2 | Bangladesh Bank (BB) |  | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
3 | Bangladesh Bureau of Educational Information and Statistics (BANBEIS) |  | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
4 | National Board of Revenue (NBR) |  | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
5 | SMS Gateway |  | Both |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
6 | iBas++ |  | Pull |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
7 | Input Output Table (IOT) |  |  |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
8 | Social Accounting Matrix (SAM) |  |  |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
9 | e-Nothi |  | Both |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document
10 | National Platform Framework (NPF) |  |  |  | GED | DRF | Collect From Website or Issue Letter form Macro Data | 5 Years Plan Document

## Common Service
Sl | Common Service Name | Related Component Module | Remarks

## Report
SL | Module | Report Name | Business Rules | Format

## WS_Int_Q
Sl | Integration Point | Is System Ready? | Push/Pull | Internal/External | Who are Using It | Why Using It | How Using It | What Are The Output | When Use It | Remarks

## SRS Checklist
Sl | Title | Status | Remarks